## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Aravind | 2025-09-11 | API returning null for user input | Sprint 2 | Aravind | Functional | Fixed input validation | 2025-09-12 | Closed | Validated
2 | Aravind | 2025-09-18 | Delay in AI response from Dialogflow | Sprint 3 | Aravind | Performance | Performance Optimized async handling | 2025-09-19 | Closed | Stable
3 | Aravind | 2025-09-25 | Middleware not handling empty payload | Sprint 4 | Aravind | Logical | Logical Added error checks | 2025-09-26 | Closed | Verified

## Sheet2
Logical
User Interface
Maintainability
Standards
Others